## README
LMS Migration, SOW Toolkit
Companion to the LMS Migration Scope of Work. Representative work sample.
Tab | What it is for
Content Audit Inventory | Log every legacy course by format, language, owner, status, and remediation call. Auto-tallies migrate / rebuild / refresh / archive counts.
Vendor Scorecard | Weighted 14-criteria rubric across 9 platforms (incl. localization and data residency). Scores, weighted totals, and the winner compute automatically.
RACI Matrix | Activity-level ownership across the program (R / A / C / I), including localization and regional compliance.
Risk Register | Live risk tracker; likelihood x impact drives an automatic severity score and a color-coded rating.
KPI Tracker | Adoption, delivery, and business-impact / ROI metrics with targets vs. actuals and automatic status flags.
Timeline (Gantt) | Phase-by-phase schedule with a visual week bar and risk ratings across a 6-month plan.
Sample rows are illustrative placeholders; replace with live project data. All totals, ratings, and status flags are live formulas.

## Content Audit Inventory
Content Audit Inventory
In a migration you move most content as is and rebuild only the legacy or compliance-critical minimum. Summary tallies update live.
Course ID | Title | Brand | Language | Format | Owner | Status | Remediation | Notes
C-001 | New Hire Onboarding | All | EN / ES | SCORM 2004 | L&D | Active | Migrate | Compatible, re-test only
C-002 | Sales Certification L1 | Brand A | EN | SCORM 1.2 | Sales Ops | Outdated | Rebuild | Legacy format
C-003 | Coach Safety & Compliance | All | EN / ES / FR | Video+PDF | Compliance | Active | Refresh | Update refs, re-brand
C-004 | Legacy POS Training | Brand B | EN | Flash | Ops | Legacy | Archive | Obsolete
C-005 | Manager Fundamentals | All | EN | xAPI | L&D | Active | Migrate | Compatible
C-006 | Product Knowledge, Equipment | Brand C | EN / DE | AICC | Product | Legacy | Rebuild | Compliance-critical
C-007 | Franchisee Ops Handbook | All | Multi | PDF | Ops | Active | Refresh | Localize 2 new markets
C-008 | Front Desk Experience | Brand A | EN | SCORM 2004 | L&D | Active | Migrate | Compatible
SUMMARY (live)
Migrate | 3
Rebuild | 2
Refresh | 2
Archive | 1
Total logged | 8
Plan target of a ~200-course library: ~120 migrate as is, ~25 rebuild, ~35 refresh, ~20 archive.

## Vendor Scorecard
Vendor Evaluation Scorecard
Weighted 14-criteria rubric across 9 platforms. Score 1 to 5; weighted average and winner compute automatically. Scores are illustrative.
# | Evaluation Criterion | Wt | Docebo | LearnUpon | Cornerstone | TalentLMS | Tovuti | LearnWorlds | Attensi | 360Learning | Whatfix
1 | Multi-Brand Functionality | 3 | 5 | 3 | 5 | 2 | 3 | 2 | 2 | 3 | 2
2 | Role-Based Access | 3 | 5 | 4 | 5 | 3 | 4 | 3 | 3 | 4 | 3
3 | Monetization Readiness | 3 | 4 | 3 | 4 | 2 | 4 | 5 | 2 | 3 | 2
4 | Content Control & Authoring | 2 | 5 | 4 | 4 | 4 | 4 | 5 | 3 | 4 | 2
5 | Certification Tracking | 3 | 5 | 4 | 5 | 3 | 4 | 3 | 3 | 4 | 2
6 | Reporting Across Brands | 3 | 5 | 3 | 5 | 3 | 4 | 3 | 3 | 4 | 3
7 | Integrations & Automation | 3 | 5 | 4 | 5 | 3 | 4 | 3 | 3 | 4 | 4
8 | User Experience & Navigation | 2 | 4 | 5 | 3 | 5 | 4 | 5 | 4 | 5 | 4
9 | Mobile Learning Access | 2 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
10 | Support & Onboarding | 2 | 4 | 4 | 3 | 4 | 4 | 4 | 4 | 4 | 4
11 | Scalability & Pricing Model | 3 | 4 | 4 | 3 | 5 | 4 | 4 | 3 | 4 | 3
12 | Security Standards | 3 | 5 | 4 | 5 | 4 | 4 | 4 | 4 | 4 | 5
13 | Multi-language / Localization | 3 | 5 | 4 | 5 | 3 | 3 | 4 | 4 | 4 | 4
14 | Data Residency & Regional Compliance | 3 | 5 | 4 | 5 | 3 | 3 | 3 | 4 | 4 | 4
| WEIGHTED AVERAGE |  | 4.7368 | 3.8158 | 4.4474 | 3.3421 | 3.7632 | 3.6316 | 3.2368 | 3.8947 | 3.2632
| Top-scoring platform (live) |  | Docebo
Weight key: 3 = high, 2 = medium. Also weigh 3-year total cost of ownership and two reference checks per vendor before final selection.

## RACI Matrix
RACI Matrix
R = Responsible, A = Accountable (one per row), C = Consulted, I = Informed.
Activity | PM | L&D | Vendor | IT / Security | Brand / Region
Readiness & content audit | A/R | C | I | C | C
Vendor selection & contract | A | C | C | C | I
Platform configuration | A | C | R | C | I
SSO & HRIS integration | A | I | C | R | I
Content migration & rebuild | C | A/R | I | I | C
Localization & regional compliance | A | R | C | C | R
Testing & pilot | A | R | C | I | C
Go-live cutover | A/R | C | C | C | R
Hypercare & KPI review | A/R | R | I | I | C

## Risk Register
Risk Register
Likelihood x Impact (1 to 3 each) drives a live severity score and a color-coded rating.
# | Risk | Likelihood | Impact | Score | Rating | Mitigation | Owner
1 | Readiness rushed or skipped | 3 | 3 | 9 | High | Gate Phase 1 on readiness sign-off; lock audit and KPIs first | PM
2 | Legacy content needs remediation | 3 | 2 | 6 | Med | Audit in Phase 0; migrate as is where valid; rebuild only the minimum | L&D
3 | SSO / integration under-scoped | 3 | 3 | 9 | High | Separate workstream, dedicated IT, +30% buffer, ownership fixed in contract | IT
4 | Localization / translation delays | 2 | 3 | 6 | Med | Lock target locales in Phase 0; translation memory; native QA per market | L&D/Region
5 | Data residency / cross-border rules | 2 | 3 | 6 | Med | Confirm regional hosting and DPAs before selection; per-region governance | IT/Legal
6 | Vendor implementation slips | 2 | 3 | 6 | Med | Milestone-based SOW with SLA; staged go/no-go gates | PM
7 | Adoption failure post-launch | 2 | 3 | 6 | Med | 48h first course, manager sign-off, regional champions, recognition | PM/Region
8 | Broken SCORM after migration | 2 | 2 | 4 | Med | Conformance test in the new LMS with 5 test accounts; pilot | L&D
9 | Platform chosen on price | 1 | 3 | 3 | Low | Select on 3-year total cost of ownership, not Year-1 price | Sponsor
Scale: Likelihood/Impact 1 (low) to 3 (high). Score = L x I. Rating: 7 to 9 High, 4 to 6 Med, under 4 Low.

## KPI Tracker
KPI Tracker
Adoption and delivery are leading indicators; business impact and ROI are lagging indicators measured through 90 days and beyond.
KPI | Target | 30-day | 60-day | 90-day | Status vs target (90d)
Adoption & delivery (leading)
Login rate (%) | 80 | 62 | 78 | 86 | On target
First-course completion (%) | 70 | 48 | 66 | 74 | On target
Certification coverage, required roles (%) | 95 | 70 | 90 | 96 | On target
Localization coverage, required locales (%) | 100 | 60 | 90 | 100 | On target
Support tickets (per 100 users) | 5 | 12 | 7 | 4 | On target
Business impact & ROI (lagging)
Time-to-competency, new hires (days) | 30 | 42 | 34 | 28 | On target
ILT / facilitator cost reduction (%) | 25 | 8 | 18 | 27 | On target
Training ROI (benefit / cost, x) | 2 | 0.8 | 1.6 | 2.3 | On target
Performance uplift, CSAT/CNPS (pts) | 5 | 1 | 3 | 6 | On target
Engagement lift vs. baseline (%) | 15 | 8 | 13 | 17 | On target
Actuals are illustrative. ROI and performance uplift are confirmed against a pre-migration baseline set in Phase 0.

## Timeline (Gantt)
Implementation Timeline
A 6-month (26-week) enterprise plan. Bars show each phase's active weeks; risk rated per phase.
Phase | Start | End | Owner | Risk | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
0 Readiness | 1 | 4 | L&D/PM | High
1 Discovery & Selection | 4 | 8 | PM/Proc | Med
2 Configuration | 8 | 14 | L&D/IT | Med
2b Integrations | 10 | 16 | IT | High
3 Content Migration | 12 | 18 | L&D | Med
4 Testing & Pilot | 18 | 22 | L&D/IT | Low-Med
5 Launch & Cutover | 22 | 24 | L&D/Comms | Low
6 Hypercare & Optimize | 24 | 26 | L&D/PM | Low
Milestones: M0 Readiness, M1 Charter, M2 Vendor, M3 Config, M4 Integrations, M5 Content, M6 Pilot, M7 Live, M8 KPI review.